# Montana Central Region Hazard Mitigation Plan

# Kick-Off Meeting Summary

March 31, 2022, 10:00-11:30 am MDT

Virtual Webinar via Zoom

#### Introductions and Opening Remarks

The State of Montana has recently undertaken an effort to create regional hazard mitigation plans covering the entire state, splitting the state into 3 separate regions each with its own hazard mitigation plan (HMP). The Central Region held a kickoff meeting for this planning process on March 31, 2022, facilitated by Wood Environment & Infrastructure Solutions, Inc. (Wood), the consulting firm hired by Montana Disaster and Emergency Services (DES) to facilitate the planning process and develop the new HMP. The meeting was held virtually via Zoom. A total of 99 people attended the webinar, primarily representing county, tribal and municipal governments as well as various stakeholders including representatives from Montana DES and the Wood consultant team. Following introductory remarks by State Hazard Mitigation Officer Sara Hartley, Jeff Brislawn, Project Manager, (Wood) began the meeting by going over the meeting agenda.

The key discussion is summarized below; additional details can be found in the meeting PowerPoint presentation. The meeting was also recorded. An interactive polling tool called Slido was used to gather feedback from the group throughout the meeting.  After an icebreaker test question, the group was polled ‘Have you participated in a hazard mitigation plan before?’  45% responded Yes and 55% No.

#### Hazard Mitigation and Resilience Planning

Scott Field with the Wood team gave a presentation on the concept of hazard mitigation planning and its importance. Mitigation is any sustained action taken to reduce or eliminate long-term risk to human life and property from natural or human-caused hazards. Mitigation Planning guides mitigation activities in a coordinated and economic manner to make Montana more disaster resilient. The U.S. Disaster Mitigation Act of 2000 requires state and local governments to draft and adopt a hazard mitigation plan, and update it every five years, to maintain eligibility for FEMA mitigation assistance grants.

Scott explained there are trends resulting in increased costs for disaster response and recovery related to population growth and the increase in the types of events we experience as a community. More people are living in hazardous areas and there is an increasing exposure of buildings, people, and infrastructure to risk, as evidenced by the increasing frequencies of billion-dollar disasters nationwide. The COVID-19 Pandemic is a good example of a circumstance that can cause a regional disruption in the community and to the economy. Scott explained we need these plans for several reasons because they reduce future recovery costs, we can plan around predictive events, and they guide mitigation activities in a coordinated manner.

Scott explained Federal Emergency Management Agency (FEMA) guidance breaks down the planning process into 9 steps:

- Step 1 Determine the Planning Area and Resources

- Step 2 Building the Planning Team

- Step 3 Create an Outreach Strategy

- Step 4 Review Community Capabilities

- Step 5 Conduct a Risk Assessment

- Step 6 Develop a Mitigation Strategy

- Step 7 Keep the Plan Current

- Step 8 Review and Adopt the Plan

- Step 9 Create a Safe and Resilient Community

In addition, the regional planning effort will follow Regional Resilience guidelines developed by the U.S. Environmental Protection Agency.  Scott described these 5 steps and how they mesh with and complement the FEMA process.

- Step 1 	Engage: Engagement for Resilience

- Step 2 	Assess: Conduct Vulnerability Assessment

- Step 3 	Act: Identify and Prioritize Strategies

- Step 4 	Fund: Fund for Action

- Step 5 	Measure: Evaluate Results and Refine Methods

##### Step 2: Hazard Mitigation Planning Committee

Step 1 has already been completed with the delineation of the regions in Montana. The Central Region Hazard Mitigation Planning Committee consists of representatives from each of the 16 counties and tribes which make up the Central Region, shown in the image below. Additionally, tribal, county, and municipal staff as well as stakeholders within each county will be participants in the planning process.  Scott noted that every update cycle is an opportunity to include additional local government participating jurisdictions, which are defined by FEMA as any entity with a governing board. This includes special service districts. Because this is a “regional” process the planning committee is structured somewhat different from local hazard mitigation plans. There is regional oversight by MT DES and within each region there will be Subregions organized to group counties with similar hazards or geography (shown below). Each County or Tribe will be asked to develop a local planning team (or LPT) that consists of municipalities and other regional or organization stakeholders. This is also where a lot of the work will be done related to developing mitigation actions.

Currently the Hazard Mitigation Planning Committee is working through Steps 3-5 of the 9-step planning process with the next steps of developing an outreach strategy, reviewing the Central Region’s capabilities, and conducting the Risk Assessment. Step 6 involves developing a mitigation strategy. Steps 7 and 8 involve final plan adoption and implementation and ensuring the adopted plan builds a safer and more resilient community.

##### Step 3: Public Outreach Strategy

FEMA requires two opportunities for public involvement during the planning process: during the draft stage and prior to plan approval. Public involvement will include online surveys during the planning effort and will look to the participating jurisdictions to assist with advertising these opportunities. In addition, the County/Tribal Planning Teams are asked to post the draft plan online and solicit comments prior to the submittal to the State and FEMA. The Wood team will be responsible for documenting this process; this may involve documenting specific meetings with stakeholders or other organizations. Counties and Tribes are encouraged to provide additional outreach beyond the regional planning outreach. An example may be noting the Regional Hazard Mitigation Plan at an already scheduled public meeting.

##### Step 4: Capabilities Assessment

Scott explained that the team will examine existing policies and programs and evaluate the effectiveness of the mitigation gaps and shortfalls to see where there are areas for improvement. He stated our team will also look at each jurisdiction’s fiscal abilities to understand where there could be funding options for mitigation not limited to grants. The capability assessment is being aligned with current FEMA planning guidance and will be an area of focus during the update.

##### Step 5: Risk Assessment

Scott discussed the three components of the risk assessment. He covered the aspects of natural hazards included in the assessment and how those hazards overlap with community assets. He discussed where there is overlap between the hazards and assets is where we have risk (e.g., potential for losses). The Montana State HMP profiled 11 hazards and ranked wildfire, flooding, and earthquake as top hazards. Most counties within the Central region also have existing HMP’s in place. These resources, as well as HMPC input will be used to develop a list of hazards which will be profiled in the plan.

The vulnerability assessment looks at a range of assets in the Region: residential/commercial structures and critical facilities and infrastructure. The Wood team will align this update with the more recent FEMA Community Lifeline framework. Understanding risks to lifeline facilities and identifying ways to minimize those risk with mitigation actions, will better position the plan for grant funding. He also stated we will look at development trends and natural resource areas in terms of assets that may warrant protection from hazard impacts.

##### Step 6: Mitigation Strategy

The Mitigation Strategy begins with reviewing the plan’s existing goals, which are broad overarching statements of what we want to achieve. Goals are supported by mitigation actions, which are specific and measurable. Goals and objectives will be updated later in the planning process. The region can choose to create one set of goals and objectives for the region as a whole, or different goals specific to each county, or both, depending on the preferences of the HMPC.

Scott shared different reference guides for mitigation action alternatives, such as FEMA’s Mitigation Ideas document and the National Flood Insurance Program Community Rating System (NFIP CRS) guidance. The HMPC will need to review and select the alternatives for new actions as part of the plan update process.  Each jurisdiction will need at least one new action, and actions will need to be prioritized.  This will be done by applying selection and prioritization criteria, such as whether it will work, is it cost-beneficial, affordable, legal, and fair etc. This process will occur at a future planning meeting/workshop.

##### Steps 7 & 8: Plan Maintenance and Adoption

Scott explained there will be three drafts of the plan: (1) Internal HMPC Review; (2) Public Review (3) State and FEMA Review. As part of the first review, the HMPC review and agree upon plan maintenance procedures. Each county, tribe, and municipality within the Central Region will need to adopt the plan to secure the buy-in for the process.

#### Objectives and Schedule for Regional Plan Update 2022

Scott reviewed the key elements of the plan update process which include, updating the risk assessment to reflect current hazards, past events and risk and vulnerability. The figure below outlines the schedule and upcoming project tasks.

The update will be developed over the next 9-12 months. The next meeting will focus on the Risk Assessment and Goals update, which will require the Wood team to conduct the assessment itself and complete the analysis. Other forthcoming deliverables include the public survey. The next 2 planning meetings will be in the summer and fall with exact dates to be determined; those meetings may be hybrid remote and in-person workshops, unless COVID Pandemic trends dictate additional web-based workshops in the future, or if the preference is for virtual workshops.

#### Roles of the Multi-County Steering Committee and County Planning Committees

The county and tribal DES Coordinators will be the main points of contact with respect to meeting logistics and coordinating local planning teams. Each Coordinator will convene a County Planning Team (CPT) or Tribal Planning Team (TPT) within each participating entity. The CPTs or TPTs will include members of appropriate departments, e.g., road and bridge, planning, public works, police/fire/public safety, and emergency management and include municipalities and could include special districts (e.g., fire and school). The coordinators will be responsible for identifying members of their HMPC and assisting with meeting logistics. The CPTs and TPTs are responsible for participating in the planning process, assisting in the updating the plans content and reviewing the draft plans to ensure it meets specific needs and local issues. Finally, each county and each tribe will need to formally adopt the plan. By doing so the plan will maintain eligibility for FEMA mitigation funds. Montana DES will provide oversight and Wood will facilitate the process, gather data, and write the plan.

Stakeholders, which include representatives from the state or federal government, private, non-profit entities or other interested organizations have various options for their level of participation:

Attending planning meetings or staying in the loop via email list

Providing data and information

Partner on mitigation efforts

Review the draft plan

#### Coordination with Other Agencies, Related Planning Efforts, and Recent Studies

A discussion was held on how to coordinate this planning process with other agencies, related planning efforts and recent studies in order to meet one of the DMA planning requirements. This is also an opportunity to develop a holistic plan and integrate related mitigation efforts where possible. No additional agencies outside of those already identified were noted during the kickoff meeting.

Additional Slido Poll Questions during the meeting are listed below, with responses in the attachment; chat and discussion is noted below:

What other significant hazard events have occurred in the past 5 years?

What other existing or recent plans, reports, or studies should be reviewed for this planning process?

Are there any upcoming opportunities for outreach at scheduled public meetings or events?

#### Initial Information Needs/Next Steps

Wood will facilitate the gathering of data and updated information from the Planning Teams. Each county and municipality will be asked to provide data based on various department inputs. This will capture recent hazard impacts, specifically those in the last five years as well as input on capability assessment updates.

GIS data collection is already in process; statewide GIS portals/data will be leveraged where possible.

Stakeholders are asked to provide additional information on hazards, related planning, and project efforts as applicable. As well as stay in the loop of the planning process via emails from the county and tribal coordinators.

Attachments: Sign in summary from Meeting Chat Log, Slido Poll results, and PowerPoint Slides

Attendees based on Chat Log input:

- Michael Bourquin

- Justin Jenness, Chief of Police, Lewiston MT

- Paul Tuss, Executive Director, Bear Paw Development Corporation

- Chris Hindoien, Mayor, City of Choteau

- Ashley Wickum, Clerk/Treasurer, Town of Chester

- Kelsey Buckley, DES Coordinator, Toole County

- Emily Alvarez, Community Planner, FEMA R8

- Sara Hartley, MT Disaster Emergency Services

- Emily Geery, Project Manager, SWCA Environmental Consultants

- Emily, City of Chinook

- Rob Pressly, Community Planner, FEMA Region 8

- Melinda Burns, DES, Pondera County

- Jeremy Springer, Director of Public Works, Town of Winnett

- Katie Brewer, Community Risk Reduction Manager, Great Falls Fire Rescue/City of Great Falls

- Ron Gleason, Interim CEO, Liberty Medical Center, Chester

- Dave Elliott, IND HEMP Ft. Benton

- Cory Calnan, State/County Cooperative Fire Protection, Montana DNRC Fire Protection Bureau

- Matt Grunenwald, Director of Campus Safety University of Providence, Great Falls

- Brad Call, Director of EM, Cascade County DES

- “Blaine County Health Department Staff x4”

- Holly Griffin, 120 AW EM

- Sara Strissel, Director of Community Planning, Bear Paw Development

- Heather Thom, RN - Fergus County Health Dept – Public Health

- Ryan Larson, Undersheriff, Toole County

- Robert Hart, Warning Coordination Meteorologist, NWS Great Falls

- Cathy Barta, Director for Strategic Development, Snowy Mountain Development Corporation (Economic Development)

- Jody Bachini, Maintenance Chief, MDT Havre Division

- Haley Velk, Blaine County DES

- Lindsay Lowe, Blaine County DES

- Robert Smith, City of Chinook

- Dolores Plumage, Blaine County Commissioner

- Frank DePriest, Blaine County Commissioner

- Curtis Harper, Glacier County DES

- Holly Phelps, City Manager for the City of Lewistown

- Donna Whitt, Sheriff, Toole County

- Jerry Lytle, Sheriff, Phillips County

- Mike Howell JB County DES

- Mandy Kelly, Clerk, Town of Stanford

- Katie Hatlelid JB County Extension

- Fred Reed, Stanford Fire Dept.

- Kendal Wilson, Fire Staff Office, Helena-Lewis and Clark National Forest

- Tim Rosette Jr, Rocky Boy Health Center EMH

- Toby Tabor, Bureau of Reclamation, Marias-Milk Rivers Division

- Hoyt Richards, Central Land Office Area Manager, MTDNRC

- Charity Yonker, Planning Director/Floodplain Administrator, Cascade County

- Richard MacDonald, Data Coordinator, Chippewa Cree Tribe

- Dan Balster, Engineer, Fergus Electric

- Cathy Sessions, PIO, Teton County Emergency Response Team

- Pete Jerrel, District 1 Foreman, Chouteau County

- Greg Speer, Phillips County DES

- Deb Gessaman, Emergency Manager, Chouteau County

- Jennifer Blansett, Deputy, Chouteau County Emergency Mgmt

- Julianne Snedigar, MSU Extension Blaine County Agent, LEPC Committee Member

- Shannon Bonney, Fire Mitigation and Education Specialist, North Central Montana District-BLM

- Nicole Erickson, Montana DES Mitigation

- Jeremy Durbin, Assistant Chief, Belt Rural Fire District

- Kevin Langkiet, Benefis Hospital

- Dave Peterson, Public Works Director, City of Havre

- Tim Bronk, Superintendent, CJI Schools

- Gina Allen, County Executive Director, Liberty County Farm Service Agency

- Steve Rose, Teton County DES and Rural Fire Chief

- Terry Tomsheck, Toole County

- Harry Barnett, Maintenance Chief, Great Falls Division MDT

- David Jones, Chief Turner Volunteer FD/Chairman Blaine County Fire Council

- Susan McEachern, DES Coordinator, MDT

- Katie Baum, Community Planner, FEMA Region 8

- Robert Skorupa, Pondera County Sheriff

- Josh Simonds, Safety and EM Preparedness Director, Logan Health

- Noah Davis, Lewistown District Manager, Northwestern Energy

- Lawrence W. Fort Benton County Shop

- Joey Zahara, MT DES

- Ryan Madsen, Bureau of Reclamation, Emergency Management Coordinator

- Kayla Johnson, Liberty County DES

- Melissa Kantorowicz, Liberty County DES/PHEP

- Robert Stevenson, Chouteau County Sanitarian

- Ryan Peterson, Fergus County DES

- Dian Brodd, Fergus County DES

- Glenna Sue Violette, Cascade County DES Assistant

- Dorothy Gremaux, 911 Supervisor/Coordinator, Central Montana 911 Center

- Jason Barkus, Assistant Chief, Havre PD

- Tom Mital, GIS Coordinator, Cascade County

- Gary Fitzgerald, Deputy Petroleum County

- Bob Vince, Wood

- Christopher Johnson, Wood PLC

- Amy Carr, Wood PLC

- Cameron Nelson, Wood PLC

- Scott Field, Wood PLC

- Natalie Schoen, Wood PLC

- Juliana Prosperi, Wood PLC

- Jeff Brislawn, Wood PLC

10:04:20 From  Hartley, Sara - MT DES  to  Everyone:

We will get started in a few more minutes.  Thank you for understanding and your time this morning.

10:13:22 From  Amy Carr - Wood  to  Everyone:

slido.com #CentralKickoff

10:15:00 From  Scott Field - Wood  to  Everyone:

Please enter your name, title, and agency/affiliation in the chat log for attendance purposes.

10:15:24 From  Justin Jenness Lewistown Police Department  to  Everyone:

Justin Jenness - Chief of Police Lewistown MT

10:15:38 From  Paul Tuss Bear Paw Development Corporation  to  Everyone:

Paul Tuss, Executive Director, Bear Paw Development Corporation

10:15:54 From  Chris Hindoien City of Choteau  to  Everyone:

Chris Hindoien, Mayor

10:15:55 From  Ashley  to  Everyone:

Ashley Wickum, Clerk/Treasurer Town of Chester

10:15:57 From  Kelsey Buckley. Toole County DES Coordinator  to  Everyone:

Kelsey Buckley - Toole County DES Coordinator

10:15:59 From  Emily Alvarez, FEMA R8 (she/her)  to  Everyone:

Emily Alvarez, Community Planner, FEMA R8

10:16:00 From  Christopher Johnson  to  Everyone:

Christopher Johnson, Hazard Mitigation Planner, Wood

10:16:01 From  Hartley, Sara - MT DES  to  Everyone:

Sara Hartley, State Hazard Mitigation Officer - MT DES

10:16:02 From  Emily Geery, SWCA Environmental Consultants  to  Everyone:

Emily Geery, Project Manager, SWCA Environmental Consultants

10:16:05 From  Emily  to  Everyone:

Emily City of Chinook

10:16:05 From  Rob Pressly, FEMA R8  to  Everyone:

Rob Pressly, Community Planner, FEMA Region 8

10:16:05 From  Pondera County DES Melinda  to  Everyone:

Melinda Burns DES Pondera County

10:16:06 From  Holly Phelps, City of Lewistown  to  Everyone:

Holly Phelps,

10:16:08 From  Jeremy Springer Dirrector of Public Works Winnett  to  Everyone:

Jeremy Springer, Director of Public Works, Town of Winnett

10:16:09 From  Chris Hindoien City of Choteau  to  Everyone:

Chris Hindoien Mayor City of Choteau

10:16:11 From  Kate Brewer Great Falls  to  Everyone:

Katie Brewer, Community Risk Reduction Manager Great Falls Fire Rescue/City of GFalls

10:16:13 From  Ron Gleason  to  Everyone:

Ron Gleason, Interim CEO Liberty Medical Center, Chester

10:16:13 From  Dave Elliott IND HEMP  to  Everyone:

Dave Elliott  IND HEMP Ft. Benton

10:16:14 From  Cory Calnan (Montana DNRC)  to  Everyone:

Cory Calnan, State/County Cooperative Fire Protection, Montana DNRC Fire Protection Bureau

10:16:16 From  Matt Grunenwald-University of Providence  to  Everyone:

Matt Grunenwald, Director of Campus Safety at the University of Providence, Great Falls

10:16:16 From  Brad Call, Cascade County DES  to  Everyone:

Brad Call, Director of Emergency Management, Cascade County DES

10:16:18 From  Blaine County Health Department  to  Everyone:

Blaine County Health Department staff X 4

10:16:21 From  Holly Griffin  to  Everyone:

Holly Griffin 120 AW EM

10:16:22 From  Sara Strissel, Bear Paw Development Corpoartion  to  Everyone:

Sara Strissel, Director of Community Planning, Bear Paw Development

10:16:22 From  Heather Thom - Fergus County Health Dept  to  Everyone:

Heather Thom, RN - Fergus County Health Dept - Public Health Director

10:16:23 From  Ryan Larson Toole County Undersheriff  to  Everyone:

Ryan Larson Toole County Undersheriff

10:16:23 From  Robert Hart - NWS Great Falls  to  Everyone:

Robert Hart, Warning Coordination Meteorologist at the National Weather Service in Great Falls

10:16:23 From  Snowy Mountain Development Corporation - Cathy Barta  to  Everyone:

Cathy Barta, Director for Strategic Development, Snowy Mountain Development Corporation (Economic Development)

10:16:24 From  Bachini, Jody - MDT Havre Division  to  Everyone:

Jody Bachini, Maintenance Chief for MDT Havre Division

10:16:26 From  BlCo DES, Commissioners, City of Chinook  to  Everyone:

Haley Velk, Blaine County DES/Lindsay Lowe, Blaine County DES/Robert Smith, City of Chinook/Dolores Plumage, Blaine County Commissioner/Frank DePriest, Blaine County Commissioner

10:16:26 From  charper  to  Everyone:

Curtis Harper, Glacier County DES

10:16:26 From  Holly Phelps, City of Lewistown  to  Everyone:

Holly Phelps, City Manager for the City of Lewistown

10:16:27 From  Sheriff Donna Whitt Toole County MT  to  Everyone:

Donna Whitt, Sheriff Toole County

10:16:28 From  Jerry Lytle  to  Everyone:

Jerry Lytle, Sheriff of Phillips County

10:16:32 From  Mike Howell JB DES  to  Everyone:

Mike Howell JB County DES, Mandy Kelly Town of Stanford Clerk, Katie Hatlelid JB County Extension, Fred Reed Stanford Fire Dept.

10:16:33 From  Kendal Wilson USFS Helena-Lewis and Clark NF  to  Everyone:

Kendal Wilson, Fire Staff Officer, Helena-Lewis and Clark National Forest

10:16:38 From  tim.rosette jr Rocky Boy Health Center  to  Everyone:

tim rosette jr Rocky Boy Health Center EMH

10:16:40 From  Toby Tabor - Reclamation  to  Everyone:

Toby Tabor, Bureau of Reclamation, Marias-Milk Rivers Division

10:16:40 From  Richards, Hoyt  to  Everyone:

Hoyt Richards, Central Land Office Area Manager, MTDNRC

10:16:40 From  Charity Yonker, Cascade County Planning Director/FP Administrato  to  Everyone:

Charity Yonker, Cascade County Planning Director/Floodplain Administrator

10:16:44 From  Richard MacDonald, Chippewa Cree Tribe  to  Everyone:

Richard MacDonald, Data Coordinator, Chippewa Cree Tribe

10:16:47 From  Dan  to  Everyone:

Dan Balster, Engineer, Fergus Electric

10:16:52 From  Cathy Sessions  Teton County  to  Everyone:

Cathy Sessions, PIO Teton County Emergency Response Team

10:16:53 From  Juliana Prosperi, Wood E&IS  to  Everyone:

Juliana Prosperi, Wood E&IS. Excited to be on the kick-off call this morning!!

10:16:54 From  Pete Jerrel chouteau county   to  Everyone:

Pete Jerrel, Chouteau County District 1 Foreman

10:16:56 From  GREG SPEER  to  Everyone:

Greg Speer Phillips County DES

10:17:00 From  Chouteau County Emergency Management/Jenn & Deb  to  Everyone:

Deb Gessaman, Emergency Manager, Jennifer Blansett, deputy, Chouteau County Emergency Management

10:17:07 From  Julianne Snedigar - MSU Extension Blaine County  to  Everyone:

Julianne Snedigar, MSU Extension Blaine County Agent, Local Emergency Planning Committee Member

10:17:11 From  Shannon Bonney-North Central Montana District BLM  to  Everyone:

Shannon Bonney-Fire Mitigation and Education Specialist-North Central Montana District-BLM

10:17:25 From  Nicole Erickson  to  Everyone:

Nicole Erickson- Montana DES Mitigation

10:17:26 From  Belt Rural FD (Jeremy Durbin)  to  Everyone:

Jeremy Durbin -Assistant chief-Belt Rural Fire District

10:17:28 From  Kevin Langkiet - Benefis Hospital  to  Everyone:

Kevin Langkiet Benefis Hospital

10:17:38 From  Amy Carr - Wood  to  Everyone:

Amy Carr, Hazard Mitigation Planner, Wood

10:17:39 From  Dave Peterson - City of Havre  to  Everyone:

Dave Peterson - Public Works Director, City of Havre

10:17:42 From  Tim Bronk - CJI Schools  to  Everyone:

Tim Bronk, Superintendent - CJI Schools

10:17:44 From  Gina Allen, Liberty County FSA  to  Everyone:

Gina Allen, County Executive Director, Liberty County Farm Service Agency

10:17:56 From  srose  to  Everyone:

Steve Rose Teton County DES and Rural Fire Chief

10:17:57 From  GREG SPEER  to  Everyone:

yes

10:18:07 From  Beverly Postma  to  Everyone:

no

10:18:11 From  TBeach  to  Everyone:

Yes

10:18:25 From  Terry Tomsheck, Toole County  to  Everyone:

Terry Tomsheck, Toole County

10:18:34 From  Harry Barnett MDT Great Falls  to  Everyone:

Harry Barnett, Maintenance Chief, Great Falls Division, Montana Department of Transportation.

10:19:35 From  Jeff Brislawn, Wood  to  Everyone:

Jeff Brislawn, Project Manager, Wood

10:20:00 From  natalie.schoen  to  Everyone:

Natalie Schoen, Entry Level Hazard Mitigation Planner, Wood

10:20:06 From  David Jones, Turner Volunteer FD / Blaine County Fire Council  to  Everyone:

David Jones, Chief Turner Volunteer FD \ Chairman - Blaine CO Fire Council

10:23:09 From  Susan McEachern, MDT  to  Everyone:

Susan McEachern, DES Coordinator MDT

10:23:11 From  Katie Baum, FEMA Region 8  to  Everyone:

Katie Baum, Community Planner, FEMA Region 8

10:23:55 From  Pondera County DES Melinda  to  Everyone:

Robert Skorupa Pondera County Sheriff is on but just on the phone  FYI

10:23:55 From  Josh Simonds - Logan Health  to  Everyone:

Josh Simonds, Safety and Emergency Preparedness Director, Logan Health

10:25:14 From  Noah Davis, Northwestern Energy  to  Everyone:

Noah Davis Lewistown District Manager, Northwestern Energy

10:27:18 From  CC District 2  to  Everyone:

Lawrence W. fort Benton county shop

10:30:04 From  Joey Zahara- MT- DES  to  Everyone:

Joey Zahara- MT-DES

10:31:03 From  Ryan Madsen, Reclamation  to  Everyone:

Ryan Madsen - Reclamation

10:36:39 From  Hartley, Sara - MT DES  to  Everyone:

And MT DES Mitigation Team will support any additional public outreach and engagement efforts

10:42:38 From  robertstevenson  to  Everyone:

….also issues with power loss for heat, communications

10:43:10 From  Hartley, Sara - MT DES  to  Everyone:

Good point Robert.  Thank you

10:44:11 From  Amy Carr - Wood  to  Everyone:

https://www.fema.gov/flood-maps/products-tools/national-risk-index

10:44:19 From  Jeremy Springer Dirrector of Public Works Winnett  to  Everyone:

Loss of power would take down our drinking water systen

10:50:07 From  Hartley, Sara - MT DES  to  Everyone:

Correct, there is no requirement to complete identified actions, just looking to see what has been completed and what jurisdictions want to complete but may be restricted by capacity or funding capabilities.  This is where we can maybe identify funding and capacity support opportunities.

10:54:58 From  Craig Crawford- Superintendent Stanford Schools  to  Everyone:

Yes, selfish, but could we look at an addition on our school that could house displaced people as a project? Like an auxiliary gym with locker rooms that could house people that are displaced and allow them a place to shower?

10:57:43 From  Hartley, Sara - MT DES  to  Everyone:

Hi Craig, that is a great question, and something I thing we should discuss further offline.  I definitely think we can find a potential funding source for a project like this, but may be difficult to fit inside our program but something we should look into a bit deeper.

11:01:45 From  Liberty County DES - Kayla + Melissa  to  Everyone:

Kayla Johnson- Liberty County DES.      Melissa Kantorowicz- Liberty County DES/PHEP

11:04:38 From  robertstevenson  to  Everyone:

Robert Stevnson Chouteau Co Sanitarian

11:06:20 From  Emily Alvarez, FEMA R8 (she/her)  to  Everyone:

School districts and special districts are eligible to adopt the plan and receive $ as a "participating jurisdiction". They just meet the same plan criteria (planning process, risk assessment, and mit strategy)

11:11:58 From  Hartley, Sara - MT DES  to  Everyone:

State DES also has a list of all wildfires over the last 5 years, and also has list of all FMAG designation

11:12:28 From  Juliana Prosperi, Wood E&IS  to  Everyone:

There was a question in the Slido Q&A about the meeting recording. We are recording this session and we will make sure the recording is made available to participants and to share with those that were not able to attend this morning's presentation. Thanks!

11:13:28 From  Dani Arps- Teton County  to  Everyone:

Wildland/Urban interface documents and CWPP docs need to be updated as well if they are heavily referenced in the HMP

11:29:53 From  Ryan and Diane Fergus County DES  to  Everyone:

Ryan Peterson, Diane Brodd Fergus County DES

11:29:53 From  Brad Call, Cascade County DES  to  Everyone:

Glenna Sue Violette-Cascade County DES Assistant

11:29:56 From  Dorothy Gremaux - Central Montana 9-1-1 Center  to  Everyone:

Dorothy Gremaux 911 Supervisor/Cordinator, Central Montana 911 Center

11:30:15 From  Jason Barkus Havre PD/LEPC  to  Everyone:

Jason Barkus Assistant Chief HavrePD

11:30:15 From  Tom Mital - Cascade County GIS  to  Everyone:

Tom Mital - GIS Coordinator, Cascade County

11:30:22 From  bill cassell  to  Everyone:

Gary Fitzgerald

11:30:36 From  bill cassell  to  Everyone:

Deputy petroleum county

11:30:43 From  Ryan Madsen, Reclamation  to  Everyone:

Ryan Madsen - Bureau of Reclamation, Emergency Management Coordinator

11:30:47 From  Dorothy Gremaux - Central Montana 9-1-1 Center  to  Everyone:

Thank you.

11:30:49 From  Matt Plagenz, USFS/Judith-Musselshell RD  to  Everyone:

Thanks for including the USFS and look forward to working with you in future.

11:30:52 From  tim.rosette jr Rocky Boy Health Center  to  Everyone:

thank you