## Schedule Yr 1
MT Central Region Hazard Mitigation Plan Project Timeline | 2022 | [11 empty] | 2023
| Feb |  | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Task 1: Organizing Resources
Central Region Initial coordination and monthly calls
Central Regional Workshop 1 Kickoff; Outreach Plan/Public Survey
Task 2: Assessing Risks and Community Vulnerabilities
Central Region HIRA drafting, Regional Workshop 2 Risk Assessment
Task 3: Develop a Mitigation Strategy
Central Region Effort, Regional Resilience Workshop 3 (series)
Task 4: Plan Adoption, Monitoring & Evaluation (Plan delivery, Public workshop)
Central Region Administrative Draft, Public Review Draft, Plan for DES Review
Central Region Final for FEMA Review, Estimated Final for Adoption
Legend |  | Monthly Meeting |  |  | Regional Workshop |  |  | Deliverable