## Slide 1
Hazard Mitigation Planning Team –
Meeting #3 – Mitigation Strategy
October 11-13, 2022 – 10:00 AM – 3:00 PM
State of Montana Central Region Hazard Mitigation Plan

## Slide 2
Agenda
Introductions
Planning process update
Review of possible mitigation activities and alternatives
Discuss criteria for mitigation action selection and prioritization
Funding mitigation options
Review of progress on existing mitigation actions (working lunch- provided)
Brainstorming Session: Development of new mitigation actions (group process)
Prioritize mitigation actions (group process)
Preview of draft HIRA
Discuss plan implementation and maintenance
Next steps

## Slide 3: Introductions

## Slide 4
Introductions
Montana Disaster and Emergency Services
  Sara Hartley – State Hazard Mitigation Officer
  Hannah Shultz – Mitigation Coordinator
  J. Lee Okeson – Central Region Supervisor
  Joey Zahara – Central Region Field Officer
  Ed Greiberis – Central Region Field Officer
County/Tribal Emergency Management Coordinators
Federal & State Partners
Other Stakeholders
Wood Project Team
  Jeff Brislawn – Project Manger
  Scott Field – Lead Planner, Central Region
  Bob Vince – Project Principal, Local Support
  Juliana Prosperi – Lead Planner, East Region
  Amy Carr – Lead Planner, West Region
  Mack Chambers – Lead GIS Analyst
  Cameron Nelson – Hazard Mitigation Specialist
  Chris Johnson – Hazard Mitigation Planner/GIS
  Natalie Schoen – Hazard Mitigation Planner
  Emily Geery – SWCA Wildfire Risk Assessment Support
  Victoria Amato – SWCA Wildfire Planning Specialist

## Slide 5
Planning Process Update

## Slide 6: FEMA’s Nine-Step Planning Process
Step 1 Determine the Planning Area and Resources
Step 2 Build the Planning Team
Step 3 Create an Outreach Strategy
Step 4 Review Community Capabilities
Step 5 Conduct a Risk Assessment
Step 6 Develop a Mitigation Strategy
Step 7 Keep the Plan Current
Step 8 Review and Adopt the Plan
Step 9 Create a Safe and Resilient Community

## Slide 7: Progress So Far
Kickoff meeting held March 31, 2022
Online public survey closed August 8th, 2022
  265 total responses received
Risk Assessment Meeting held August 17th, 2022
GIS analysis & mapping completed
Draft HIRA being completed

## Slide 8
Review of Possible Mitigation Activities and Alternatives

## Slide 9
Reduce the future demand for, and rising costs of, disaster response and recovery.
Retrofit a critical facility, enforce building codes, land use planning, remove a structure from a hazard area.
Hazard Mitigation Examples

## Slide 10
► Alter
► Avert
► Adapt
► Avoid
Review Mitigation Alternatives

## Slide 11
► Alter the Hazard
  Prescribed burns or fuels management to reduce wildfire intensity and severity
  Draining lakes behind weakened dams
Review Mitigation Alternatives

## Slide 12
► Avert the Hazard
  Floodwalls and gates
  Debris Nets and Basins
  Drainage improvements
  Channels and culverts
  Firebreaks
Review Mitigation Alternatives

## Slide 13
► Avoid the Hazard
  Acquisition
  Relocation
  Open space
  Land use designation
  Natural system protection
Review Mitigation Alternatives

## Slide 14
► Adapt to the Hazard
  Building codes
  Construction standards
  Land use and development regulations
  Design standards
  Monitoring and warning systems
  Safe rooms and shelters
Review Mitigation Alternatives

## Slide 15
Mitigation Action Categories
  Prevention
  Structural projects
  Public information
  Property protection
  Natural resource protection
  Emergency services

## Slide 16
FEMA Community Lifelines

## Slide 17
Defensible space
Structural protection through ignition-resistant construction activities
Hazardous fuels reduction activities
  Community level vegetation management
  Vegetation removal
  Vegetation clearing and/or thinning
  Slash removal
  Vertical clearance of tree branches
Biomass Plant
Projects Eligible for FEMA Funding - Wildfire

## Slide 18
Acquisition
Dry and wet flood-proofing
Elevation
Minor localized flood reduction projects
  Detention ponds
  Channel stabilization
New policy change: levee projects if no duplication of programs with Army Corps
Infrastructure retrofit
  Culverts, bridges, etc.
Projects Eligible for FEMA Funding - Flood Mitigation

## Slide 19
Ensure development and enforcement of building codes for snow loads
Burying/hardening overhead power lines
Informing the public about severe winter weather impacts
Organizing outreach to vulnerable populations including establishing and promoting accessible heating centers
Retrofitting public buildings to withstand snow loads and prevent roof collapse
Projects Eligible for FEMA Funding – Winter Storm

## Slide 20
Landslides/geologic hazards
  Channel or slope stabilization - protection of critical facilities
  Property acquisition
Utility protection/ infrastructure retrofit
Safe rooms
Generators
Microgrids/smart grids
Seismic building/infrastructure retrofit
Climate resilient mitigation activities
  Groundwater recharge
  Green infrastructure
Projects Eligible for FEMA Funding (Other Hazards)

## Slide 21
“Conduct routine maintenance…”
“Develop a program…”
“Conduct a study…”
“Improvements were recently completed on…”
“Identify projects to reduce risk…”
Things FEMA Will Not Count Towards The Requirement

## Slide 22
Discuss Criteria for Mitigation Action Selection and Prioritization

## Slide 23
STAPLEE
Social
Technical
Administrative
Political
Legal
Economic
Environmental
Other Things to Consider
Life Safety
Vulnerable Populations
Addressing High Risk Hazards
Protect Critical Facilities/Assets
Multiple Goals/Hazards
Mitigation Action Selection and Prioritization

## Slide 24
Funding Mitigation Options

## Slide 25
Funding Sources
      Federal & state grants
      Local/tribal budgets
      Capital improvement budget
      Healthcare Coalition
      Public-private partnerships
      Conservation coalitions
      Fees/assessments/levies
      Other?

## Slide 26
FEMA Hazard Mitigation Grants
      Projects must be tied directly to the mitigation goals, objectives, and specific actions in your HMP.
      Most have 25% local match
        HMGP: Hazard Mitigation Grant Program, post-disaster, all natural hazards
        HMGP Post-Fire: available following an FMAG declaration
        PA 406: Public Assistance Program Section 406, post-disaster, add mitigation measures to PA projects to avoid/reduce future damage
        BRIC: Building Resilient Infrastructure & Communities, pre-disaster/annual cycle, all natural hazards, infrastructure emphasis
        FMA: Flood Mitigation Assistance, pre-disaster/annual cycle, flood hazard, NFIP insured structures & communities
        HHPD: High Hazard Potential Dam Program, pre-disaster/annual cycle, for non-Federal high hazard dams rated Unsatisfactory. (local match varies)

## Slide 27
FEMA Preparedness Grants
      Emergency Management Performance Grant
      Homeland Security Grant Program
      Tribal Homeland Security Grant
      Nonprofit Security Grant
      Transit Security Grant/Intercity Bus Security Grant
      Port Security Grant
      Assistance to Firefighters Grants
      Regional Catastrophic Grant Program
      National Earthquake Hazards Reduction Program Grant
      Community Assistance Program

## Slide 28
Other Grants
      US DOT
      BIA
      HUD
      EPA
      USDA
      USFW
      CDC
      BOR
      USACE
      NOAA/NWS
      SBA
      State of Montana grants?

## Slide 29
Review of Progress on Existing Mitigation Actions

## Slide 30
Mitigation Actions from Previous Plans
# | Jurisdiction | Action/Project Name & Description | Hazards Mitigated | Lead Agency | Partner Agencies | Cost Estimate | Potential Funding Sources | Schedule/ Timeline | Old Priority
1.1 | Chester | Address repeated road and property flash flooding by enhancing storm-water drainage system | Flood | City of Chester |  | High | City of Chester, MT DES, FEMA |  | High
1.2 | Chester | Replace the one existing siren for the city, enhance coverage for whole city. | All | City of Chester, | County DES | Meduim | City of Chester, County |  | Medium
1.3 | Chester | Continue participation in NFIP. Find assistance to administer regulations so that development complies | Flood | City of Chester, | County DES | Medium | City of Chester, MT DES, Co DES |  | Medium
2.1 | Liberty County | Identify methods, adopt, and educate people on how to receive warning/alert information. | All | County Commissioners, | City of Chester, LEPC, County DES | Low | Existing budgets |  | High
2.2 | Liberty County | Manage forest fuels on Mt. Royal communications site | Wildland Fire | County Fire Warden, | County Commissioners | Medium | DNRC, County, MT DES |  | High
2.3 | Liberty County | Update the hazardous materials flow study | Hazmat | LEPC, | County DES | Medium | FEMA, MT DES, County DES |  | High
2.4 | Liberty County | Offer a CPR and First Aid course | All | Hospital, | LEPC | High | Hospital Attendees |  | High
2.5 | Liberty County | Complete rural addressing system and install fireproof road signs | All | County Planning and Road Dept |  | High | County |  | Medium
2.6 | Liberty County | Continue to enhance radio availability. | All | County |  | Medium | County DES and Fire, MT DES, DNRC |  | Medium
2.7 | Liberty County | Purchase radios for Joplin | All | County Commissioners, | DES | Medium | County, DNRC |  | Medium
2.8 | Liberty County | Educate school children on what to during a natural disaster | All | County DES, | LEPC | Low | Existing budgets |  | Medium

## Slide 31
Prior Mitigation Actions
Not Started: Work has not begun
In Progress: Work has begun but is not completed
Completed: The action has been finished
Annual Implementation: Ongoing with no specific end date
Deleted: The action is no longer relevant or cancelled due to changing priorities, lack of funds, etc.
There is no requirement or expectation to have completed any/all previous actions.

## Slide 32
Break into groups by County/Tribe.
Spreadsheets showing the actions from your previous plans will be distributed.
Review and update the status of those actions you can.
  We don’t expect 100% today
  …but we will need 100% before we can submit to FEMA.
Make notes of who you may need to follow up with after the meeting.
Electronic copies will be emailed out next week.
Activity: Mitigation Status Updates

## Slide 33
Mitigation Actions Status Update
2022 Status
  Not Started
  In Progress
  Completed
  Annual Implementation
  Deleted
2022 Priority
  High
  Medium
  Low
2022 Implementation Notes
  When was it completed?
  Why are you deleting it?
  What has been accomplished so far?
  What roadblocks have prevented implementation?
Update other columns where possible
  Schedule/Timeline
  Budget
  Partner Agencies
  Etc.

## Slide 34
Development of New Mitigation Actions

## Slide 35
► Must have at least one new action
► Must have at least one action for each applicable hazard
► Must be “true” mitigation to meet FEMA requirements
► Preparedness & response actions may also be included
► Must address one or more mitigation goals/objectives
► Actions must be prioritized
► Actions must have detail on implementation & administration
► Actions must have a basic review of benefit vs cost
► Must include actions that address existing and future development
Disaster Mitigation Act Requirements

## Slide 36
The mitigation strategy is a “wish list”
not a commitment of resources.
New Mitigation Actions Are Not “Binding”

## Slide 37
Reduce impacts to people, property, the environment, and the economy from hazards.
Protect community lifelines and critical infrastructure to ensure the continuity of essential services.
Increase public awareness and participation in hazard mitigation.
Sustain and enhance jurisdictional capabilities to enact mitigation activities.
Integrate hazard mitigation into other plans, processes, and regulations.
Promote regional cooperation and leverage partnerships in mitigation solutions where possible.
DRAFT Central Region Mitigation Goals

## Slide 38
Goals
General guidelines that explain what you want to achieve
Usually broad policy/vision statements
Objectives (optional)
Define strategies or implementation steps to attain goals
Specific and measurable
Actions
Specific projects/activities to achieve goals & objectives
Mitigation Strategy Elements

## Slide 39
Central Region Hazards – DRAFT Significance Rankings
Hazard | Geographic Area | Magnitude/ Severity | Probability | Significance
Communicable Disease | Extensive | Critical | Occasional | Medium
Cyber-Attack | Significant | Critical | Likely | Medium
Dam Failure | Significant | Critical | Occasional | Medium
Drought | Extensive | Critical | Likely | Medium
Earthquake | Significant | Limited | Likely | Low
Flooding | Limited | Critical | Likely | Medium
Hazardous Material | Limited | Negligible | Likely | Low
Landslide | Limited | Negligible | Likely | Low
Severe Summer Weather | Extensive | Limited | Highly Likely | Medium
Severe Winter Weather | Extensive | Critical | Highly Likely | High
Human Conflict | Significant | Limited | Occasional | Low
Tornadoes/Windstorms | Extensive | Limited | Highly Likely | Medium
Transportation Accidents | Limited | Limited | Highly Likely | Low
Volcanic Ash | Extensive | Limited | Unlikely | Low
Wildland/Rangeland Fire | Extensive | Critical | Highly Likely | High

## Slide 40
FEMA Community Lifelines

## Slide 41
► Draft Hazard Identification & Risk Assessment
► Handout on action alternatives by hazard & category
► Public survey input
► Water protection & usage plans, watershed plans, drainage plans, etc.
► Capital Improvement Plan
► Community Wildfire Protection Plan
► FEMA ‘Mitigation Action Portfolio’ publication
  https://www.fema.gov/sites/default/files/2020-08/fema_mitigation-action-portfolio-support-document_08-01-2020_0.pdf
Sources of Ideas for Mitigation Actions

## Slide 42
Public Survey Results
Chart: 
| Electrical Power Grid Resiliency | Public Education/Awareness | Indoor/Outdoor Warning | Generators for Critical Facilities | Improve Reliability of Communication | Windbreaks & Snow Fences | Wildfire Defensible Space | Public Health Incident Preparedness | Severe Weather Shelters | Critical Facilities Protection | Wildfire Fuels Treatment | Water Conservation | Evacuation Route Development | Flood Mitigation | Stormwater Drainage Improvement | Land Use Planning | Forest Health/Watershed Protection | Stream Stabilization/Restoration | Dam Safety | Education & Discounts on Flood Insurance | Access to Flood Insurance | Floodprone Property Buyout | Landslide Mitigation | Rockfall Mitigation
 | 146 | 129 | 125 | 116 | 111 | 101 | 92 | 91 | 90 | 83 | 83 | 72 | 65 | 60 | 60 | 55 | 46 | 45 | 39 | 38 | 32 | 14 | 8 | 4
Please indicate the types of mitigation actions that you think should have the highest priority.

## Slide 43
Suggested Ideas for New Mitigation Actions
Provide indoor NOAA weather radios to critical facilities, community shelters, city facilities, schools and other identified areas.
Install additional snow fences at strategic locations to minimize roadway impacts and transportation incidents
Create a water conservation public awareness and educational campaign, including educational materials on water conservation measures to implement during drought periods.
Implement the high priority projects identified in CWPPs
Notification system for tourists for thunderstorms, fire, floods, and dam failure as visitors may not get emergency notifications on their phones.
Strategic grassland fuels reduction efforts surrounding vulnerable communities
Ensure critical communication infrastructure is grounded to mitigate lightning strikes.

## Slide 44
What new mitigation actions should be added to the Plan?
Write one idea for each new action on a blank worksheet
You are encouraged to collaborate with other agencies or jurisdictions
Include details where you can, but it’s okay if you don’t know or can elaborate later.
Include the Jurisdiction and Lead Agency
Feel free to submit more than one
Review each other’s suggestions
Activity: Develop New Mitigation Actions

## Slide 45
Prioritization of Mitigation Actions

## Slide 46
STAPLEE
Social
Technical
Administrative
Political
Legal
Economic
Environmental
Other Factors to Consider
Life safety
Addressing high risk hazards
Protect critical facilities
Multiple goals/hazards
Vulnerable populations and equity
Mitigation Action Selection and Prioritization

## Slide 47
Connect the Dots!
4 Dots per Person
Indicate which should be priority mitigation actions with a dot, keeping STAPLEE Criteria in mind
Dots will later be converted into a High, Medium, Low initial prioritization
Activity: New Mitigation Action Prioritization
Notes: What we will talk about today.

## Slide 48
Preview of Draft HIRA

## Slide 49
DRAFT Hazard Identification & Risk Assessment
Coming soon for planning team review
It is critical we get your feedback and input – it’s YOUR plan!
Review both for the region as a whole and for your jurisdiction specifically
Feedback will be incorporated into full draft and resent for review

## Slide 50
Regional HMP Table of Contents
Introduction
Community Profile
Planning Process
Hazard Identification & Risk Assessment
Mitigation Strategy
Plan Implementation & Maintenance
Jurisdictional Annexes
Appendices

## Slide 51
HIRA Contents
Hazard Identification
  Disaster Declaration History
  Hazards Considered
  Methodology
  Climate Change
  Hazard Rankings/Summary
Assets At Risk
  Population
  General Property
  Critical Facilities & Lifelines
  Cultural, Historical and Natural Resources
Hazard Profiles

## Slide 52
Hazard Profiles
Hazard Description
Geographical Area Affected
Past Events
Magnitude/Severity
Frequency/Likelihood of Occurrence
Vulnerability Assessment
Risk Summary

## Slide 53
Hazard Vulnerability Assessments
People
Property
Critical Facilities & Lifelines
Economy
Historic & Cultural Resources
Natural Resources
Development Trends

## Slide 54
Plan Implementation and Maintenance

## Slide 55
The plan must describe how, when, and by whom the plan will be:
  Monitored:
    Tracking implementation of mitigation actions
    Identifying new actions as needed
    Losses avoided due to mitigation activities
  Evaluated
    Effectiveness at achieving goals and objectives
    What hindered implementation?
    What factors contributed to success?
  Updated
    Reviewed & revised at least once every five years.
  Continued Public Involvement
    Engaged and given opportunity to provide input
Plan Implementation & Maintenance

## Slide 56
The following tasks should be conducted “regularly”, at least annually
  HIRA review – changes to hazards or vulnerabilities
  Review of recent hazard incidents
  Updates on mitigation actions
  Assess effectiveness of completed mitigation actions
Annual face to face meeting of Hazard Mitigation Planning Team to discuss updates on mitigation actions and/or significant impactors/events
  Target is first quarter of each year?
Job aids:
  Sample agenda for annual meeting in appendix
Plan Implementation & Maintenance

## Slide 57
Mitigation is most successful when it is incorporated into the day-to-day functions and priorities of government and development.
Implementation through existing plans and/or programs is recommended wherever possible:
  Comprehensive Plan
  Zoning/Subdivision Ordinances
  Floodplain Ordinance
  Capital Improvements Plan
  Emergency Operations Plan
Discussion: Provide at least one opportunity to incorporate or cross reference the HMP into other planning mechanisms
Incorporation into Other Planning Mechanisms
FEMA Requirement – Element C6
a. Does the plan identify the local planning mechanisms where hazard mitigation information and/or actions may be incorporated?
b. Does the plan describe each community’s process to integrate the data, information, and hazard mitigation goals and actions into other planning mechanisms?
c. The updated plan must explain how the jurisdiction(s) incorporated the mitigation plan, when appropriate, into other planning mechanisms as a demonstration of progress in local hazard mitigation efforts.

## Slide 58
Next Steps

## Slide 59
Project Schedule
Project Milestones | Anticipated Timeline
Meeting #2 HIRA review | August
Meeting #3 Mitigation Strategy | October
HIRA Draft for HMPC review | October
Full Draft for HMPC review | November
Public Review Draft | December
DHSEM Review Draft | January – February 2023
Final Plan for FEMA Review (estimated) | March – April 2023
Final Approved HMP for local adoption | May-July 2023

## Slide 60
Next Steps
Please return Plan Update Guide if you haven’t already
Provide input on mitigation action statuses
Submit additional new mitigation actions
Review and comment on HIRA and full draft plan when available
Think about what local-level Objectives you may want to adopt to supplement the plan’s Goals
Stay informed by email of upcoming meetings

## Slide 61
wsp.com
Questions? Thank you!
Lead Planner
Scott Field
Wood Environment & Infrastructure Solutions, Inc
Scott.field@woodplc.com
720-569-9266
Project Manager
Jeff Brislawn
Wood Environment & Infrastructure Solutions, Inc
Jeff.brislawn@woodplc.com
303-704-5506
Central Region Project Manager/
Mitigation Coordinator
Hannah Shultz
Montana DES
Hannah.Shultz@mt.gov
406-292-1092